## Sheet1
Sl # | Task | Owner | End Date | Completion (%) | Impediments | Pending work
1 | Develop Engine for document classification and content extraction | Shuvrangshu, Bishwadeep | 2020-08-31 | 10 | No | OCR extraction, NLP
2 | Develop UI application to upload the documents and show the content extracted by the engine, followed by verification and final submission. | Prateek, Mithun | 2020-08-31 | 10 | No | Upload document Show extracted data and validate Admin Dashboard
3 | Create API to save the browsed file in DB, pass it to the Classification engine and return the extracted response | Debajyoti, Prosenjit | 2020-08-31 | 50 | No | Integration with UI and Classification Engine